## Comm Mgt Plan Template
Communications plan template for project: Develop an Application (App) to Provide Real-Time Marketing Data
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Project Kickoff Meeting | Project Manager | Project Team Members | Project Initiation | In-Person Meeting | Introduce the project, clarify roles, discuss objectives.
Weekly Status Reports | Project Manager | Key Stakeholders | Weekly | Email | Provide project updates, progress, and upcoming tasks.
Change Requests | Project Manager | Change Control Board | As Required | Change Request Form | Submit and review change requests for approval.
Project Review Meetings | Project Manager | Project Team Members | Monthly | In-Person Meeting | Assess progress, discuss challenges, plan improvements.
Vendor Updates | Project Manager | Vendor | As Needed | Email/Phone Meetings | Communicate project requirements and monitor vendor performance.
Version: 01 |  |  | Date: