## Quality Mgt Plan Template
Quality management plan for project: Develop an Application (App) to Provide Real-Time Marketing Data
Part I: Project objectives (reference project charter)
1 Develop an application to provide marketing data in real-time.
2 Gather information and data to better understand the target market and develop strategies in real-time.
3 Enable product development and phase-out decisions, improved pricing analysis, increased sales, improved customer satisfaction, and acceleration of new product launch decisions.
4
5
6
7
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Keiko Tanaka | QA processes |  | X
Priya Service | IT Lead |  |  | X
Ram Samuels | Marketing Director |  |  | X
Cary Manning | Project Manager |  |  | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Develop and Implement Quality Management Plan |  |  | Perform Testing and Validation
Conduct Quality Audits |  |  | User Acceptance Testing (UAT)
Review and Approve Quality Documentation |  |  | Defect Tracking and Resolution