## Risk Register Template
Project: Develop an Application (App) to Provide Real-Time Marketing Data Date: 20XX
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Vendor faces production delays due to high demand from other clients. | Delayed Vendor Deliverables |  | External Vendor | T | 5 | 3 | 15 |  | Allocate additional time for vendor delays and adjust project schedule accordingly.
2 | Frequent changes in project requirements due to evolving market demands | Scope Creep |  | Project Manager | T | 5 | 5 | 25 |  | Prioritize critical features and negotiate with stakeholders
3 | Insufficient encryption and data protection measures. | Data Security Breach |  | IT Lead | T | 5 | 1 | 5 |  | Activate an incident response plan
4 | Team member receives a better job offer from a competitor. | Key Team Member Turnover |  | Project Manager | T | 3 | 1 | 3 |  | Identify potential replacements
5 | Lack of user involvement during the requirements gathering phase. | Insufficient User Adoption |  | Marketing Director | T | 3 | 3 | 9 |  | Offer incentives for user adoption
6 | Integration with legacy systems causes conflicts. | Technology Compatibility Issues |  | IT Lead | T | 3 | 1 | 3 |  | Collaborate with vendors and technical experts
7
Total Risk Score | [7 empty] | 60 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low