## Template
|  | 1.0 All Hands Project |  |  | Level 1 Project level
1.1 Design Phase | 2.1 Development Phase |  | 3.1 Test Phase | 4.1 Launch and Approve the App Phase | Level 2 Phase level
1.1.1 Define Key App Functionality Requirements | 2.1.1 Develop Initial Prototype |  | 3.1.1 Test the Final App Prototype | 4.1.1 Launch the New App | Level 3 Work package level
1.1.2 Identify Vendor to Design and Develop App | 2.1.2 Perform Prototype Beta Test |  | 3.1.2 Begin Full-Scale Development of the App | 4.1.2 Monitor App Performance
1.1.3 Solicit Initial Design Feedback | 2.1.3 Update Prototype Based on Feedback |  | 3.1.3 Begin IT Hiring for App Support | 4.1.3 Implement App Upgrades
1.1.4 Develop Initial Design | 2.1.4 Gain Prototype Sign-off |  | 3.1.4 Train Marketing Personnel | 4.1.4 Launch App v2
1.1.5 Gain Final Design Approval | 2.1.5 Develop App Launch Plan |  | 3.1.5 Approve the App Launch | 4.1.5 Document Any App Issues